## Sheet1
Sprint 2 - 14 Days
Dublin Bikes Features & Functions | Work Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Create a Google Maps API R + Z + V | 25 | bar: Day 1 to Sprint 2 - 14 Days Day 14
a) All members create Maps API
b) Set up an API key, test on app.py
c) Save API key offline (local machine)
Weather API - R | 25 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 3 | 1 | 1
a) All members create OpenWeather API
b) Rhys create OpenWeather function
c) Test API key on OpenWeather and verify
HTML/CSS V | 5 | Day 1: 2; Sprint 2 - 14 Days Day 3: 3; Sprint 2 - 14 Days Day 6: 1; Sprint 2 - 14 Days Day 7: 1; Sprint 2 - 14 Days Day 8: 1; Sprint 2 - 14 Days Day 9: 5; Sprint 2 - 14 Days Day 14: 1
a) Edit html file to include JS script
Migrate EC2 to new EC2 - Zaur | 15 | bar: Day 1 to Sprint 2 - 14 Days Day 8; Sprint 2 - 14 Days Day 10 to Sprint 2 - 14 Days Day 14
a) Connect
b) SSH into EC2
FLASK | 15 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1
a) Rhys create flask app.py
b) Everyone contribute to adding functions and decorators
c) Zaur connect new EC2 to flask | 10 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 1 | 2 | 3 | 2 | 2 | 2
d) Test flask app on EC2 to verify web server
b) Keep branches up to date
Meeting notes - ZAUR | 40 | 1 | 1 | 1 |  | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1
a) 5 x meetings per week (30 mins) - ZAUR log
b) Start an SRS - ZAUR
c) Start a Dbikes report journal - ZAUR
Make burndown charts - ZAUR
Time Taken | 130 | 9 | 6 | 9 | 6 | 9 | 9 | 8 | 5 | 10 | 7 | 8 | 9 | 8 | 8
111
[13 empty] | Zaur | Victoria | Rhys
[13 empty] | 29.2105 | 34.6875 | 38.2759